## Sheet1
MILESTONE 1
BOT: DESIGN |  | Week 1 : Sept 15- Sept 22
Due Sept 22 | Deliverable |  | Item/Status | Issues/Tasks | Team Members | Estimated Date | Actual Date
1 | Problem Statement | Identifying the problem | Discussing idea and brainstorming | #1 | All | 2016-09-18 | 2016-09-18
|  | Writing idea as statement | How to verbally construct it | #1 | All | 2016-09-18 | 2016-09-18
2 | Bot Description | Bot functionality - Scope | Discussing idea and brainstorming | #2 | All | 2016-09-18 | 2016-09-18
|  | Bot functionality - Technology | Deciding which technology to finalize | #2 | All | 2016-09-18 | 2016-09-18
3 | Design Sketches | Storyboard | Drawing storyboard diagram | #3 | Sohan | 2016-09-21 | 2016-09-21
|  | Wireframe | Drawing wireframe diagram | #3 | Sunil Gautam | 2016-09-21 | 2016-09-21
4 | Architecture Design | Designing architecture | Drawing architecture diagram | #4 | Pranav Ajay | 2016-09-21 | 2016-09-21
|  | Writing description |  | #4 | Pranav Ajay | 2016-09-21 | 2016-09-21
5 | Additional Patterns | Writing description |  | #5 | All | 2016-09-21 | 2016-09-21
MILESTONE 1 | Week 2: Sept 23- Sept 30
BOT: DESIGN
Due Sept 22 | Deliverable |  | Item/Status | Issues/Tasks | Team Members | Estimated Date | Actual Date
1 | Use Cases | UC 1 | Brainstorming and Writing Use case | #1.1 | Gautam Sohan | 2016-09-30 | 2016-09-30
|  | UC 2 | Brainstorming and Writing Use case | #1.2 | Sunil Sohan | 2016-09-30 | 2016-09-30
|  | UC 3 | Brainstorming and Writing Use case | #1.3 | Ajay Sunil | 2016-09-30 | 2016-09-30
2 | Mocking | Mock data | Json /DB / any tool | #2 | All | 2016-09-30 | 2016-10-02
|  | Mock Json | Structuring Json | #2 | Pranav | 2016-09-30 | 2016-10-02
3 | Bot inplementation | Bot setup |  | #3 | Gautam | 2016-09-30 | 2016-09-30
|  | Handling inputs and replies on slack | bot replies and user questions | #4 | Gautam | 2016-09-30 | 2016-09-30
Week 3: Oct 1-Oct 7
| Deliverable |  | Item/Status | Issues/Tasks | Team Members | Estimated Date | Actual Date
1 | Mocking | Mock json reads and writes |  | #5 | Pranav Sohan | 2016-10-07 | 2016-10-07
|  | Mock json bug fixes |  | #5 | All | 2016-10-07 | 2016-10-07
2 | Bot Implementation | Logic Development | Basic control flow | #6 | All | 2016-10-07 | 2016-10-06
|  | User commands |  | #7 | Gautam Sunil | 2016-10-07 | 2016-10-07
|  | Error Handling |  | #8 | Sohan Ajay | 2016-10-07 | 2016-10-07
3 | Selenium Testing | Start to plan selenium testing |  | #9 | Sohan Ajay Sunil | 2016-10-07 | 2016-10-08
Week 4: Oct 8-Oct 14
| Deliverable |  | Item/Status | Issues/Tasks | Team Members | Estimated Date | Actual Date
1 | Mocking | Mock json bug fixes |  | #5 | Sohan | 2016-10-09 | 2016-10-10
2 | Bot Implementation | user conversation code |  | #10 | Gautam | 2016-10-09 | 2016-10-09
|  | Finding meeting slot |  | #11 | Pranav | 2016-10-11 | 2016-10-11
|  | Add/ Remove team member |  | #12 | Sunil | 2016-10-09 | 2016-10-09
|  | Cancel meeting |  | #13 | Ajay | 2016-10-14 | 2016-10-14
3 | Selenium Testing | Getting x paths |  | #14 | All | 2016-10-04 | 2016-10-14
Week 4: Oct 8-Oct 14
| Deliverable |  | Item/Status | Issues/Tasks | Team Members | Estimated Date | Actual Date
1 | Mocking | Mock json bug fixes | In review | #5 | Pranav | 2016-10-09 | 2016-10-10
2 | Bot Implementation | Coding the user conversation flow |  | #10 | Gautam | 2016-10-09 | 2016-10-09
|  | Handling meeting slot |  | #11 | Pranav | 2016-10-11 | 2016-10-11
|  | Add/ Remove team member json binding |  | #12 | Sunil | 2016-10-09 | 2016-10-09
|  | Cancel meeting and validations |  | #13 | Ajay | 2016-10-14 | 2016-10-14
3 | Selenium Testing | Use Case 1 |  | #1.1 | Sunil | 2016-10-14 | 2016-10-14
|  | Use Case 2 |  | #1.2 | Sohan
|  | Use Case 3 |  | #1.3 | Ajay
Week 5: Oct 14-Oct 21
| Deliverable |  | Item/Status | Issues/Tasks | Team Members | Estimated Date | Actual Date
| Mocking | Mock json bug fixes |  | #5 | Pranav | 2016-10-16 | 2016-10-18
| Bot Implementation | Coding the user conversation flow and review |  | #10 | Gautam | 2016-10-16 | 2016-10-18
|  | Handling meeting slot and review |  | #11 | Pranav | 2016-10-16 | 2016-10-18
|  | Add/ Removefunctionality |  | #12 | Sunil | 2016-10-16 | 2016-10-18
|  | Cancel meeting and validations |  | #13 | Ajay | 2016-10-16 | 2016-10-18
| Selenium Testing | Use Case 1 |  | #1.1 | Sunil | 2016-10-16 | 2016-10-18
|  | Use Case 2 |  | #1.2 | Sohan | 2016-10-16 | 2016-10-18
|  | Use Case 3 |  | #1.3 | Ajay | 2016-10-14 | 2016-10-14
| Screencast |  |  | #14 | All | 2016-10-20 | 2016-10-20